## RN
Business area | Project | Category | RFQ/Prequalification date | Plan. start | Procurement value- (MSEK)
RN Rural | Substation Brattströmmen - Civil works/Site preparation | Civil works | 2025-12-01 | 2026 Q3 | < 10
RN Stockholm | Primary substation Bredäng - New GIS 220kV station- Electrical work | New switchgear | 2026-01-01 | 2026 Q3 | > 300
RN Rural | Klovsten. Renewal ledning, byte delvsis till kabel | New overheadline | 2026-02-01 | 2026 Q3 | > 100
RN Rural | OHL Enån-Laforsen 2*2km 145kV with steel tower EPC | New overheadline | 2026-03-01 | 2027 Q1 | > 50
RN Rural | Substation Repbäcken 145 kV | Renewal of switchgear | 2026-04-01 | 2027 Q1 | > 200
RN Rural | Substation Brattströmmen 130 kV/50 kV EPC | New switchgear | 2026-04-01 | 2027 Q2 | > 100
RN Rural | Substation Ulvsby & Grava FS 30/10 KV | Renewal of switchgear | 2026-04-01 | 2026 Q4 | > 20
RN Stockholm | FUT Älvsjö | Cable excavation | 2026-05-01 | 2028 Q4 | < 100
RN Rural | OHL Bollnäs "triangle" . 145 kV. 28km wooden poles | New overheadline | 2026-06-01 | 2027 Q2 | > 300
RN Rural | Substations Bollnäs "triangle" 3 stations New-build and 1 station Re-build 145 kV (Nordsyd program) | New switchgear | 2026-06-01 | 2027 Q2 | > 250
RN Rural | Substation Väse 130kV - Re-build EPC | Renewal of switchgear | 2026-08-01 | 2026 Q3 | >100
RN Rural | Substation Grönviken 145 kV new bays EPC | Renewal of switchgear | 2026-09-01 | 2027 Q2 | < 100
RN Stockholm | Substation Liljeholmen 11/33/110kV GIS excl Transfromers | New switchgear | 2026-10-01 | 2027 Q2 | > 700
RN Rural | OHL Njutånger – Betberg (2x11 km steel tower) | New overheadline | 2027-02-01 | 2027 Q3 | > 100
RN Rural | OHL Bollnäs "triangle" . 145 kV. 17km composite poles / 2*3km steel tower. (Nordsyd program) | New overheadline | 2027-05-01 | 2027 Q2 | > 300
RN Rural | OHL Njutånger – Söderala (42 km stålportal/Gitter-steel) | New overheadline | 2027-09-01 | 2028 Q1 | > 200

## LN
Business area | Project | Category | RFQ/Prequalification date | Plan. start | Procurement value- (MSEK)
LN Stockholm | Lillsjö-Bromma 0,4-11 kV and 33kV | Cable excavation | 2026-01-01 | 2026 Q2 | > 20
LN Stockholm | Söder om Fs Ulvsunda | Cable excavation | 2026-03-01 | 2026 Q2 | > 50
LN Stockholm | OB MV LUF söder om Fs Bromsten | Cable excavation | 2026-03-01 | 2026 Q2 | > 30
LN Stockholm | Täby LUF 2 | Cable excavation | 2026-02-01 | 2026 Q3 | > 100
LN Stockholm | MV Brantholmsbacken | Cable excavation | 2026-02-01 | 2026 Q2 | > 30
LN Stockholm | MV Sätra | Cable excavation | 2026-02-01 | 2026 Q3 | > 20
LN Stockholm | MV Orhems Koloniområde | Cable excavation | 2026-02-01 | 2026 Q4 | > 50
LN Stockholm | Gamla Tyresövägen | Cable excavation | 2026-03-01 | 2026 Q2 | > 30
LN Stockholm | MV Armémuseum + Norrlandsgatan | Cable excavation | 2026-03-01 | 2026 Q4 | > 50
LN Stockholm | Djursnäs Station 10-20kV | Cable excavation | 2026-03-01 | 2026 Q4 | > 20
LN Stockholm | Ekerö Tätort | Cable excavation | 2026-03-01 | 2026 Q4 | > 50
LN Stockholm | MV Tidaholmsvägen | Cable excavation | 2026-03-01 | 2026 Q4 | > 20
LN Stockholm | MV 11kV Finn Malmgrens väg | Cable excavation | 2026-06-01 | 2026 Q4 | > 20
LN Stockholm | Södra Färingsö | Cable excavation | 2026-08-01 | 2027 Q2 | > 30
LN Stockholm | MV Redundance Hillersjö | Cable excavation | 2026-09-01 | 2026 Q3 | > 20
LN Stockholm | FS Vällingby slinga | Cable excavation | 2026-09-01 | 2026 Q3 | > 20
LN Stockholm | FS Koltorp – FS Torsvik | Cable excavation | 2026-04-01 | 2027 Q1 | > 20
LN Stockholm | Nynäshamn kablifiering 1 | Cable excavation | 2026-10-01 | 2027 Q1 | > 75
LN Stockholm | MV Renathvägen/Pastellvägen | Cable excavation | 2026-10-01 | 2027 Q1 | > 30